## CommercializationActivities
Commercialization Activities
Stage 1 | Technical Analysis | Market Needs Assessment | Venture Assessment
Investigation | Step 1 | Step 2 | Step 3
| Define concept | Conduct market overview | Estimate profit potential
| Confirm critical assumptions | Identify pricing structure (value in use) | Conduct self, enterprise commercialization assessments
| Survey state of the art | Identify market barriers | Identify professional needs
| Identify critical barriers | Identify risks | Identify capital needs (at least through Stage 2, only)
| Evaluate critical applicability |  | Determine assets (IP, people, needs)
Determine technology
Stage 2 | Technical Feasiblity | Market Study | Economic Feasiblity
Feasiblity | Step 4 | Step 5 | Step 6
| Test feasibility of technology | Identify & quantify: Market size | Formulate financial assumptions
| Design working model and test | Identify & quantify: Customers | Develop pro forma financial statements
| Assess preliminary producibilty | Identify & quantify: Volume | Identify seed capital and long-term funding strategy
| Conduct manufacturing assessment | Identify & quantify: Prices | Form advisory team
| Assess safety & environmental features | Identify & quantify: Distribution | Develop route-to-market (license, start-up)
|  | Identify & quantify: Competitors | Develop exit strategy
Stage 3 | Engineering Prototype | Strategic Market Plan | Strategic Business Plan
Development | Step 7 | Step 8 | Step 9
| Develop prototype | Identify marketing team and target market | Decide venture, license, intellectual property
| Identify materials and processes | Select market channels | Identify management team, organization structure
| Conduct tests, develop manufacturing methods | Field test | Write business plan
Stage 4 | Pre-Production Prototype | Market Validation | Business Start-Up
Introduction | Step 10 | Step 11 | Step 12
| Develop production prototype and process | Establish market relationships | Establish business function
| Select manufacturing equipment | Conduct limited sales and analyze sales | Hire staff
| Design field support system | Survey customers | Execute contracts
| Demo product features | Refine marketing plan | Secure first-stage financing
Stage 5 | Production | Sales and Distribution | Business Growth
Growth | Step 13 | Step 14 | Step 15
| Prepare commercial design | Expand distribution | Monitor enterprise position
| Establish quality control | Analyze competitor response | Hire and train personnel
| Construct facilities | Assess customer satisfaction | Execute contracts
| Conduct full production | Assess distributor satisfaction | Arrange financing
| Finalize internal distribution system | Refine product features | Institute vision, mission, and management policies
Stage 6 | Production Support | Market Diversification | Business Maturity
Maturity | Step 16 | Step 17 | Step 18
| Maximize production | Develop market retention | Establish SWOT process
| Establish after-market support | Establish market scan | Invest profits
| Warrantee service | Identify new markets | Monitor product life cycle, business trends
| Implement training program | Identify new products | Monitor management technologies
Implement innovations

## Responsibilities
Commercialization Activities
Stage 1 | Technical Analysis |  | Market Needs Assessment |  | Venture Assessment
Investigation | Step 1 |  | Step 2 |  | Step 3
| Define concept | Client, SBDC, SCORE, DelEasi | Conduct market overview | Client, SBDC, Bill, Konrad, Lerner School, library search | Estimate profit potential | Client, SBDC, Bill, Konrad, UD student projects
| Confirm critical assumptions | UD faculty, DelEasi, SCORE, lirbrary search | Identify pricing structure (value in use) | Client, SBDC, Bill, Konrad, UD student projects | Conduct self, enterprise commercialization assessments | Client, SBDC, Bill, Konrad, UD student projects
| Survey state of the art | OEIP (Bill, Konrad), library search | Identify market barriers | Client, SBDC, Bill, Konrad, UD student projects | Identify professional needs | Client, SBDC, Bill, Konrad, UD student projects
| Identify critical barriers | OEIP (Bill, Konrad), SCORE, DelEasi, UD Faculty | Identify risks | Client, SBDC, Bill, Konrad, UD student projects | Identify capital needs (at least through Stage 2, only) | Client, SBDC, Bill, Konrad, UD student projects
| Evaluate critical applicability | OEIP (Bill, Konrad), SCORE, DelEasi, UD Faculty |  |  | Determine assets (IP, people, needs) | Client, SBDC, Bill, Konrad, UD student projects
| Determine technology | OEIP (Bill, Konrad), SCORE, DelEasi, UD Faculty
Stage 2 | Technical Feasiblity |  | Market Study |  | Economic Feasiblity
Feasiblity | Step 4 |  | Step 5 |  | Step 6
| Test feasibility of technology | Client, OEIP, SCORE, DelEasi, UD faculty | Identify & quantify: Market size | Client, SBDC, Bill, Konrad, UD student projects | Formulate financial assumptions | Client, SBDC, Bill, Konrad
| Design working model and test | Client, OEIP, SCORE, DelEasi, UD faculty | Identify & quantify: Customers | Client, SBDC, Bill, Konrad, UD student projects | Develop pro forma financial statements | Client, SBDC, Bill, Konrad
| Assess preliminary producibilty | DEMEP | Identify & quantify: Volume | Client, SBDC, Bill, Konrad, UD student projects | Identify seed capital and long-term funding strategy | Client, SBDC, Bill, Konrad
| Conduct manufacturing assessment | DEMEP | Identify & quantify: Prices | Client, SBDC, Bill, Konrad, UD student projects | Form advisory team | Client, SBDC, Bill, Konrad
| Assess safety & environmental features | SCORE, DelEasi, DEMEP | Identify & quantify: Distribution | Client, SBDC, Bill, Konrad, UD student projects | Develop route-to-market (license, start-up) | Client, SBDC, Bill, Konrad
|  |  | Identify & quantify: Competitors | Client, SBDC, Bill, Konrad, UD student projects | Develop exit strategy
Stage 3 | Engineering Prototype |  | Strategic Market Plan |  | Strategic Business Plan
Development | Step 7 |  | Step 8 |  | Step 9
| Develop prototype |  | Identify marketing team and target market |  | Decide venture, license, intellectual property
| Identify materials and processes |  | Select market channels |  | Identify management team, organization structure
| Conduct tests, develop manufacturing methods |  | Field test |  | Write business plan
Stage 4 | Pre-Production Prototype |  | Market Validation |  | Business Start-Up
Introduction | Step 10 |  | Step 11 |  | Step 12
| Develop production prototype and process |  | Establish market relationships |  | Establish business function
| Select manufacturing equipment |  | Conduct limited sales and analyze sales |  | Hire staff
| Design field support system |  | Survey customers |  | Execute contracts
| Demo product features |  | Refine marketing plan |  | Secure first-stage financing
Stage 5 | Production |  | Sales and Distribution |  | Business Growth
Growth | Step 13 |  | Step 14 |  | Step 15
| Prepare commercial design |  | Expand distribution |  | Monitor enterprise position
| Establish quality control |  | Analyze competitor response |  | Hire and train personnel
| Construct facilities |  | Assess customer satisfaction |  | Execute contracts
| Conduct full production |  | Assess distributor satisfaction |  | Arrange financing
| Finalize internal distribution system |  | Refine product features |  | Institute vision, mission, and management policies
Stage 6 | Production Support |  | Market Diversification |  | Business Maturity
Maturity | Step 16 |  | Step 17 |  | Step 18
| Maximize production |  | Develop market retention |  | Establish SWOT process
| Establish after-market support |  | Establish market scan |  | Invest profits
| Warrantee service |  | Identify new markets |  | Monitor product life cycle, business trends
| Implement training program |  | Identify new products |  | Monitor management technologies
Implement innovations